## Sprint 1
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 1 | Dates: Sep 3, 2015 - Sep 17, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Program Display | As a player, I want to be able to play the game in any screen sizing that I want. | As a player I want to be able to have a defualt small size on first launch. | yuchen | The program launches using the default sizing. | done
|  | As a plyaer I want to be able to select from a list of screen sizes. | yuchen | Screen sizing is implemented into the menu. | done
| As a player, I want be able to pick up items to increase the power of my weapon. | As a player I want to see clearly what the item is before picking it up. | michael | Items are consumed when the player moves over them. | in progress | implementing in progress, collisions are working but the items changes to the weapons are not in place
|  | As a player I want to be able to recognize the item without needing to pause gameplay | michael | The item is seen and moving around in the game. | pending | item abilities are awaitng until the weapons are in place
|  | As a player I want to see what the effect is of the weapon immediately. | michael | Weapon effects are visually seen on the client screen. | pending | item abilities are awaitng until the weapons are in place
User Input | As a player, I want to play with only using keyboard. | As a player, I want to use common keys for input in this game. | younouss | The player ship is responding to user input. | done
Data Modeling | As a player, I want to see how long I have been on the current level. |  | yuchen | The timer is connected to the interface. | done
| As a player, I want to be able to see all different ships attributes, such as: speed, weapon power, special weapons, etc. | As a player I want to see what the speed of the ship is. | will | A ship is available for use in the gameset that acts independent of the other ships. | done
| As a player, I want to know a history of my friends scores and my scores on a leaderboard, that tracks them. | As a player I want to see the weapons of the ship. | Ryan | The leader board displays with the played games. | done
Menu | As a player I want a start screen to load when the game starts |  | brian | A main screen is presented to the player on the game start. | done
| As a player I want to be able to adjust the options. | As a player I want to be able to adjust the options. | brian | Options are changed in real time after selection by the user. | in progress | pending implementation of other menu objects
HUD | As a player, I want a simple HUD that displays my score that does not get in the way of the gameplay. | As a player I want a simple HUD that displays my score. | brian | The HUD overlays on the main level and displays content to the user. | in progress | area blocked out for use with score
|  | As a player I want a HUD that displays my health | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration with the ship
|  | As a player I want a HUD that displays my upgrades. | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration of the items
Ships | As a player, I want different playable ships that feel unique. | As a player I want a default ship to be used if I am unfamiliar with the ships in the game. | will | When the game is started the default ship is created and controlable by the user. | in progress | other ships have images and some stats are in place for other ships
|  | As a player, when my ship explodes, I loss all my powers but a fraction of the power ups that I collected are released in various directions. | will | Upgrades are scattered back onto the screen for re-picking up. | pending | pending item upgrades working
Enemies | As a player, I want to have a variety of enemies in the game with interesting behavior. | As a player I want a easy grunt type of enemy. | will | A simple enemy is able to be used for debugging for filling the level for an easy opponent. | pending | pending implementation of the ship, as it inherts from there
Level | As a player, I want multiple unique levels. | As a player I want a background for the level. | ryan | The background is available and scrolls with the player movement. | done | Level back ground is working
|  | As a player I want enemies to spawn on the screen and attack me | ryan | Enemies are able to spawn into the level given their starting coordinates. | pending | pending on enemies implementation
|  | As a plyer I want to be challenged on the level | ryan | Enemies are able to take more damage or move quicker on the level. | pending | pending on enemies implementation, and difficulty settings
|  | As a player I want to see new enemies come onto the screen | ryan | Enemies are able to move onto the screen from off screen as if out of line of sight and not appearing from magic. | pending | pending enemies implementation

## Sprint 2
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 2 | Dates: sep. 17, 2015 - Oct. 1, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Program Display
| As a player, I want be able to pick up items to increase the power of my weapon. | As a player I want to see clearly what the item is before picking it up. | michael | Items are consumed when the player moves over them. | pending | implementing in progress, collisions are working but the items changes to the weapons are not in place. Pending the different weapons are implemented
|  | As a player I want to be able to recognize the item without needing to pause gameplay | michael | The item is seen and moving around in the game. | pending | item abilities are waiting until the unique weapons are in working
|  | As a player I want to see what the effect is of the weapon immediately. | Younouss | Weapon effects are visually seen on the client screen. | in progress
| As a player I want to be able to adjust the options. | As a player I want to be able to adjust the options. | brian | Options are changed in real time after selection by the user. | in progress | pending implementation of other menu objects
HUD | As a player, I want a simple HUD that displays my score that does not get in the way of the gameplay. | As a player I want a simple HUD that displays my score. | brian | The HUD overlays on the main level and displays content to the user. | done | area blocked out for use with score
|  | As a player I want a HUD that displays my health | brian | The HUD overlays on the main level and displays content to the user. | done | display working, pending integration with the ship
|  | As a player I want a HUD that displays my upgrades. | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration of the items
Ships | As a player, I want different playable ships that feel unique. | As a player I want a default ship to be used if I am unfamiliar with the ships in the game. | will | When the game is started the default ship is created and controlable by the user. | done | other ships have images and some stats are in place for other ships
|  | As a player, when my ship explodes, I loss all my powers but a fraction of the power ups that I collected are released in various directions. | will | Upgrades are scattered back onto the screen for re-picking up. | done | items need to be expanded to interact with the weapon system
Enemies | As a player, I want to have a variety of enemies in the game with interesting behavior. | As a player I want a easy grunt type of enemy. | Ryan | A simple enemy is able to be used for debugging for filling the level for an easy opponent. | done | waiting on weapon system to use for attacking player
Level
|  | As a player I want enemies to spawn on the screen and attack me | ryan | Enemies are able to spawn into the level given their starting coordinates. | in progress | enemies do not currently attack, waiting on weapon system
|  | As a plyer I want to be challenged on the level | ryan | Enemies are able to take more damage or move quicker on the level. | pending | pending on difficulty settings
|  | As a player I want to see new enemies come onto the screen | ryan | Enemies are able to move onto the screen from off screen as if out of line of sight and not appearing from magic. | done | enemies are destroyed with outside the bounds of the game
Tutorial | As a player, I want to have a tutorial on how to play the game. |  | Yuchen |  | in progress | generic tutorial in place until image is used later
User Input | As a player, i want to play with only using a mouse. |  | Younouss |  | in progress
| As a player, I want to be able to enter cheats. |  | Younouss |  | pending | pending on difficulty settings/external settings

## Sprint 3
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 3 | Dates: Oct. 1, 2015 - Oct. 15, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Program Display
| As a player, I want be able to pick up items to increase the power of my weapon. | As a player I want to see clearly what the item is before picking it up. | michael | Items are consumed when the player moves over them. | done
|  | As a player I want to be able to recognize the item without needing to pause gameplay | michael | The item is seen and moving around in the game. | done
|  | As a player I want to see what the effect is of the weapon immediately. | michael | Weapon effects are visually seen on the client screen. | in progress | base level bullets are implementd, higher level bullets are not
| As a player I want to be able to adjust the options. | As a player I want to be able to adjust the options. | brian | Options are changed in real time after selection by the user. | in progress | pending implementation of other menu objects
HUD | As a player, I want a simple HUD that displays my score that does not get in the way of the gameplay. | As a player I want a HUD that displays my upgrades. | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration of the items
Ships | As a player, I want different playable ships that feel unique. |  | will | Other ships are able to be played | done | needs to be cleaned up due to introduction of bugs
| As a player, I want to be able to see all different ships attributes, such as: speed, weapon power, special weapons, etc. |  | will | The selection screen displays | done | needs to be cleaned up due to introduction of bugs
Enemies | As a player, I want to have a variety of enemies in the game with interesting behavior. | As a player I want enemies to spawn on the screen and attack me | ryan | Enemies are able to spawn into the level given their starting coordinates. | in progress | enemies do not currently attack, waiting on weapon system
|  | As a plyer I want to be challenged on the level | ryan | Enemies are able to take more damage or move quicker on the level. | done | api hooks created for use for weapon and ship classes to damage enemies
Level | As a player, I want to have the ability to select different difficulty settings. |  | Ryan | Enemies take different amounts of damge or certain weapon types to deal extra damage | pending | waiting on higher level weapons to be implemented
Tutorial | As a player, I want to have a tutorial on how to play the game. |  | Yuchen | The user is able to learn how to play | done
| As a player, I want to be able to read what each weapons does. |  | Yuchen | The user can either pause or hover over the item or upgrade to see what it does | pending | pending all items integrated
| As a player, I want to see information about the enemies on the level. |  | Yuchen | The user can eitehr pause or over over a enemy to see what it does | in progress | the pause portion works for the game
User Input | As a player, i want to play with only using a mouse. |  | Younouss | the mouse can be used as the only input device for the game | in progress | mouse input works, bugs have been introduced from the additonal ships implemented
| As a player, I want to be able to enter cheats. |  | Younouss | cheats can change or do different effects on the game | pending | pending on difficulty settings/external settings
Audio | As a player, I want exciting sounds/music. |  | Brian | sound is playing on the game and loops properly | in progress | not able to be implemented this sprint

## Sprint 4
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 3 | Dates: Oct. 1, 2015 - Oct. 15, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Program Display |  | As a player I want to see what the effect is of the weapon immediately. | michael | Weapon effects are visually seen on the client screen. | in progress | base level bullets are implementd, higher level bullets are not
| As a player I want to be able to adjust the options. | As a player I want to be able to adjust the options. | brian | Options are changed in real time after selection by the user. | in progress | pending implementation of other menu objects
HUD | As a player, I want a simple HUD that displays my score that does not get in the way of the gameplay. | As a player I want a HUD that displays my upgrades. | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration of the items
Enemies | As a player, I want to have a variety of enemies in the game with interesting behavior. | As a player I want enemies to spawn on the screen and attack me | ryan | Enemies are able to spawn into the level given their starting coordinates. | in progress | enemies do not currently attack, waiting on weapon system
Level | As a player, I want to have the ability to select different difficulty settings. |  | Ryan | Enemies take different amounts of damge or certain weapon types to deal extra damage | pending | waiting on higher level weapons to be implemented
| As a player, I want to be able to read what each weapons does. |  | Yuchen | The user can either pause or hover over the item or upgrade to see what it does | pending | pending all items integrated
| As a player, I want to see information about the enemies on the level. |  | Yuchen | The user can eitehr pause or over over a enemy to see what it does | in progress | the pause portion works for the game
User Input | As a player, i want to play with only using a mouse. |  | Younouss | the mouse can be used as the only input device for the game | in progress | mouse input works, bugs have been introduced from the additonal ships implemented
| As a player, I want to be able to enter cheats. |  | Younouss | cheats can change or do different effects on the game | pending | pending on difficulty settings/external settings
Audio | As a player, I want exciting sounds/music. |  | Brian | sound is playing on the game and loops properly | in progress | not able to be implemented this sprint