## Sprint 1
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 1 | Dates: Sep 3, 2015 - Sep 17, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Program Display | As a player, I want to be able to play the game in any screen sizing that I want. | As a player I want to be able to have a defualt small size on first launch. | yuchen | The program launches using the default sizing. | done
|  | As a plyaer I want to be able to select from a list of screen sizes. | yuchen | Screen sizing is implemented into the menu. | done
| As a player, I want be able to pick up items to increase the power of my weapon. | As a player I want to see clearly what the item is before picking it up. | michael | Items are consumed when the player moves over them. | in progress | implementing in progress, collisions are working but the items changes to the weapons are not in place
|  | As a player I want to be able to recognize the item without needing to pause gameplay | michael | The item is seen and moving around in the game. | pending | item abilities are awaitng until the weapons are in place
|  | As a player I want to see what the effect is of the weapon immediately. | michael | Weapon effects are visually seen on the client screen. | pending | item abilities are awaitng until the weapons are in place
User Input | As a player, I want to play with only using keyboard. | As a player, I want to use common keys for input in this game. | younouss | The player ship is responding to user input. | done
Data Modeling | As a player, I want to see how long I have been on the current level. |  | yuchen | The timer is connected to the interface. | done
| As a player, I want to be able to see all different ships attributes, such as: speed, weapon power, special weapons, etc. | As a player I want to see what the speed of the ship is. | will | A ship is available for use in the gameset that acts independent of the other ships. | done
| As a player, I want to know a history of my friends scores and my scores on a leaderboard, that tracks them. | As a player I want to see the weapons of the ship. | Ryan | The leader board displays with the played games. | done
Menu | As a player I want a start screen to load when the game starts |  | brian | A main screen is presented to the player on the game start. | done
| As a player I want to be able to adjust the options. | As a player I want to be able to adjust the options. | brian | Options are changed in real time after selection by the user. | in progress | pending implementation of other menu objects
HUD | As a player, I want a simple HUD that displays my score that does not get in the way of the gameplay. | As a player I want a simple HUD that displays my score. | brian | The HUD overlays on the main level and displays content to the user. | in progress | area blocked out for use with score
|  | As a player I want a HUD that displays my health | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration with the ship
|  | As a player I want a HUD that displays my upgrades. | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration of the items
Ships | As a player, I want different playable ships that feel unique. | As a player I want a default ship to be used if I am unfamiliar with the ships in the game. | will | When the game is started the default ship is created and controlable by the user. | in progress | other ships have images and some stats are in place for other ships
|  | As a player, when my ship explodes, I loss all my powers but a fraction of the power ups that I collected are released in various directions. | will | Upgrades are scattered back onto the screen for re-picking up. | pending | pending item upgrades working
Enemies | As a player, I want to have a variety of enemies in the game with interesting behavior. | As a player I want a easy grunt type of enemy. | will | A simple enemy is able to be used for debugging for filling the level for an easy opponent. | pending | pending implementation of the ship, as it inherts from there
Level | As a player, I want multiple unique levels. | As a player I want a background for the level. | ryan | The background is available and scrolls with the player movement. | done | Level back ground is working
|  | As a player I want enemies to spawn on the screen and attack me | ryan | Enemies are able to spawn into the level given their starting coordinates. | pending | pending on enemies implementation
|  | As a plyer I want to be challenged on the level | ryan | Enemies are able to take more damage or move quicker on the level. | pending | pending on enemies implementation, and difficulty settings
|  | As a player I want to see new enemies come onto the screen | ryan | Enemies are able to move onto the screen from off screen as if out of line of sight and not appearing from magic. | pending | pending enemies implementation

## Sprint 2
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 2 | Dates: sep. 17, 2015 - Oct. 1, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Program Display
| As a player, I want be able to pick up items to increase the power of my weapon. | As a player I want to see clearly what the item is before picking it up. | michael | Items are consumed when the player moves over them. | in progress | implementing in progress, collisions are working but the items changes to the weapons are not in place
|  | As a player I want to be able to recognize the item without needing to pause gameplay | michael | The item is seen and moving around in the game. | pending | item abilities are awaitng until the weapons are in place
|  | As a player I want to see what the effect is of the weapon immediately. | Younouss | Weapon effects are visually seen on the client screen. | pending | item abilities are awaitng until the weapons are in place
| As a player I want to be able to adjust the options. | As a player I want to be able to adjust the options. | brian | Options are changed in real time after selection by the user. | in progress | pending implementation of other menu objects
HUD | As a player, I want a simple HUD that displays my score that does not get in the way of the gameplay. | As a player I want a simple HUD that displays my score. | brian | The HUD overlays on the main level and displays content to the user. | in progress | area blocked out for use with score
|  | As a player I want a HUD that displays my health | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration with the ship
|  | As a player I want a HUD that displays my upgrades. | brian | The HUD overlays on the main level and displays content to the user. | in progress | display working, pending integration of the items
Ships | As a player, I want different playable ships that feel unique. | As a player I want a default ship to be used if I am unfamiliar with the ships in the game. | will | When the game is started the default ship is created and controlable by the user. | in progress | other ships have images and some stats are in place for other ships
|  | As a player, when my ship explodes, I loss all my powers but a fraction of the power ups that I collected are released in various directions. | will | Upgrades are scattered back onto the screen for re-picking up. | pending | pending item upgrades working
Enemies | As a player, I want to have a variety of enemies in the game with interesting behavior. | As a player I want a easy grunt type of enemy. | Ryan | A simple enemy is able to be used for debugging for filling the level for an easy opponent. | done | pending implementation of the ship, as it inherts from there
Level
|  | As a player I want enemies to spawn on the screen and attack me | ryan | Enemies are able to spawn into the level given their starting coordinates. | in progress | enemies do not currently attack
|  | As a plyer I want to be challenged on the level | ryan | Enemies are able to take more damage or move quicker on the level. | pending | pending on difficulty settings
|  | As a player I want to see new enemies come onto the screen | ryan | Enemies are able to move onto the screen from off screen as if out of line of sight and not appearing from magic. | done | pending enemies implementation
Tutorial | As a player, I want to have a tutorial on how to play the game. |  | Yuchen |  | in progress | image file that is in use
User Input | As a player, i want to play with only using a mouse. |  | Younouss
| As a player, I want to be able to enter cheats. |  | Younouss