## Sprint 1
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 1 | Dates: Feb. 5, 2015 - Feb. 12, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Event Managment | As a student I want to register for instructor events | As a studnent I want to see all the proffesors that have open events so that I can see if my instructor has an event |  |  | Completed
|  | As a student I want to see all of a instructors events so I can know what events are available | Lynn | Page is accessible and show correct data | Completed
|  | As a student I want to see all available slots for and event so I can choose which is the best time for me | Lynn | Page is accessible and show correct data | Not implemented | User roles not implemented yet.
|  | As a student I want to reserver a spot for myself so that I know I will be able to meet | Lynn | Slot is assigned in database | Completed
| As an Instructor I want to cancel my events | As a student I want to have a user registration page so that I can register myself as a user | Lynn | Page is accessible | Completed
|  | As a student I want to have a user registration form on the user registration page so that I can register myself as a user | Lynn | Form with all needed fields is viewable Form is nicely styled | Completed
|  | As a student I want to be able to submit a registration request to the system so that I receive a confirmation email from the system | Stanislav | Registration request was successfully submitted and email with the confirmation link received | Not implemented
|  | As a student I want to be able to receive an email so that I can confirm my email address is a valid email address | Unassigned | Confirmation link was received. Upon opening the link, student was verified and able to access their profile | Not implemented
Login page | As a student I want to be able to login so that I can access my profile | As a student I want to have a login page so that I can login | Lynn | Page is accessible | Completed
|  | As a student I want to have a login form on the login so that I can login | Lynn | Form with all needed fields is viewable Form is nicely styled | Completed
|  | As a student I want to be able to login to the system so that I can access my profile | Stanislav | Student inputed the credentials and was able to access the profile | Not implemented
| As an instructor I want to be able to login so that I can access my profile | As an instructor I want to have a login page so that I can login | Lynn | Page is accessible | Completed
|  | As an instructor I want to have a login form on the login page so that I can login | Lynn | Form with all needed fields is viewable Form is nicely styled | Completed
|  | As a instructor I want to be able to login to the system so that I can access my profile | Stanislav | Instructor inputed the credentials and was able to access the profile | Not implemented
Chat page | As a professor, I want to allow my students to be able to ask me questions instantly when I am available so that I can better help them. | As a professor I want to have a chat webpage so that I can send chat messages | Travis | There must be a page available to professors to enter messages | In progress | Basic chat mechanism implemented. Individual user roles not implemented. The chat is open to all users.
|  | As a professor I want to have a chat interface so that I can send chat messages | Travis | Professors must have an interface for entering messages | In progress
|  | As a professor I want to be able to send chat messages so that all the participants of the chat can see them | Travis | Messages must be sent to all other chat participants | In progress
|  | As a professor I want to specify my name so that participants can easily identify me | Travis | Messages must include a user name | In progress
| As a student, I want to be able to ask my professors questions instantly when they are available so that I can get help when I need it. | As a student I want to have a chat webpage so that I can send chat messages | Travis | There must be a page available to students to enter messages | In progress | Basic chat mechanism implemented. Individual user roles not implemented. The chat is open to all users.
|  | As a student I want to have a chat interface so that I can send chat messages | Travis | Students must have an interface for entering messages | In progress
|  | As a student I want to be able to send chat messages so that all the participants of the chat can see them | Travis | Messages must be sent to all other chat participants | In progress
|  | As a student I want to specify my name so that participants can easily identify me | Travis | Messages must include a user name | In progress
Main (index) page | As any user of the website I want to be able to access website's main interface so that I can view website's functionality | As any user I want to have a link to the login page | Erik | Link is accessible | Completed | needs to be converted to jsf/outcome button
|  | As any user I want to be able to view departmanetal news so that I am aware of what is coming up | Erik | News link is accessible | Not Implemented | News page has not been created yet. Template is implemented.
|  | As any user I want to have a link to the chat page | Erik | Link is accessible | Completed | needs to be converted to jsf/outcome button
|  | As any user I want to see well designed user intarface so that I can enjoy using the webiste | Erik | Interface is pretty | Completed
|  | As any user I want a navigation bar to move about the website | Erik | Nav bar is accessible from every page | Completed | needs to be converted to jsf/outcome button
Texbook Database | As a student, I want to know what textbooks are required for each class
|  | As a student I want to search for specific classes to see the required text | Brian |  | Complete
Navigation Rule | As any user of the website I want to be placed in the right page whenever I clicked buttons or change pages | As a student I want to have all pages that I can accessed within my account's permission | Thuy | Navigation rule created in faces-config and xmls | Completed | Need to implement when all the pages created

## Sprint 2
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 2 | Dates: Feb. 12, 2015 - Feb. 19, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Event Managment | As a professor I want to create an event so that other people may scheduel time with me | As a professor I want to have an event creation page so that I can create a new event | Lynn | Page is accessible | Completed
|  | As a professor I want a newly created event to be permenatly stored, so that I and others can view events later | Lynn | When form is submited, a Proper Database record is strored | Incomplete | Faculty ID is not stored in the record yet
|  | As an proffessor I want to view my created events, so that I can know which events have been created | Lynn | Page is accessible, and nicely styled | Incomplete | More Styling Needed
| As a proffesor, when I create an event I want the right amount of timeslots to be automatically created, so that other can view the available timeslots | As a proffesor I want the number of time slots for an event to be automatically calculated so that I don't have to create individual slots myself | Lynn | Amount of slots are properly calculated and insterted in to the database | Completed
|  | As a proffesor I want to be able to view the timeslots for each event | Lynn | Slots for each Event, are displayed and nicely styled | Incomplete | More Styling needed
Login page | As a student I want to be able to login so that I can access my profile
|  | As a student I want to be able to login to the system so that I can access my profile | Stanislav | Student inputed the credentials and was able to access the profile | Completed
As an instructor I want to be able to login so that I can access my profile
|  | As a instructor I want to be able to login to the system so that I can access my profile | Stanislav | Instructor inputed the credentials and was able to access the profile | Completed
As an administrator I want to be able to login so that I can access my profile
|  | As a administrator I want to be able to login to the system so that I can access my profile | Stanislav | Instructor inputed the credentials and was able to access the profile | Completed
Registration page | As a professor I want to register so that I can utilize the services provided by CS website
|  | As an administrator I want to be able to add an instructor to the system so that he can start using the CS website | Stanislav | When form is submited the input verified If valid information is submitted a new user is created in the database | Not implemented | User roles not implemented yet.
As a student I want to register so that I access services provided by CS website
|  | As a student I want to be able to submit a registration request to the system so that I receive a confirmation email from the system | Stanislav | Registration request was successfully submitted and email with the confirmation link received | Not implemented
|  | As a student I want to be able to receive an email so that I can confirm my email address is a valid email address | Stanislav | Confirmation link was received. Upon opening the link, student was verified and able to access their profile | Not implemented
Texbook Database | As a student, I want to have a convinient way to see the texbooks reqired for courses I am interested in
|  | As a student I want to search for specific classes to see the required text | Brian |  | Complete
|  | As a student I want to be able to see the required text for all available classes on one page | Brian |  | Complete
Chat page | As a professor, I want to allow my students to be able to ask me questions instantly when I am available so that I can better help them. | As a professor I want to have a chat webpage so that I can send chat messages | Travis | There must be a page available to professors to enter messages | In progress | Basic chat mechanism implemented. Individual user roles not implemented. The chat is open to all users. Bugs from sprint 1 fixed.
|  | As a professor I want to have a chat interface so that I can send chat messages | Travis | Professors must have an interface for entering messages | In progress
|  | As a professor I want to be able to send chat messages so that all the participants of the chat can see them | Travis | Messages must be sent to all other chat participants | In progress
|  | As a professor I want to specify my name so that participants can easily identify me | Travis | Messages must include a user name | In progress
|  | As a professor I want to be able to see my chat history so that I can see what I discussed with my students | Travis | Chat history must be saved for the chat session | In progress
| As a student, I want to be able to ask my professors questions instantly when they are available so that I can get help when I need it. | As a student I want to have a chat webpage so that I can send chat messages | Travis | There must be a page available to students to enter messages | In progress | Basic chat mechanism implemented. Individual user roles not implemented. The chat is open to all users. Bugs from sprint 1 fixed.
|  | As a student I want to have a chat interface so that I can send chat messages | Travis | Students must have an interface for entering messages | In progress
|  | As a student I want to be able to send chat messages so that all the participants of the chat can see them | Travis | Messages must be sent to all other chat participants | In progress
|  | As a student I want to specify my name so that participants can easily identify me | Travis | Messages must include a user name | In progress
|  | As a student I want to be able to see my chat history so that I can see what I discussed with my professors | Travis | Chat history must be saved for the chat session | In progress
Navigation Bar | As a user, I want to see pages that are related to my user role. | As an unregistered user, I was to see the other pages I can navigate to. | Erik | There must not be any pages visible to unregistered user that are exclusive to student/admin/instructor, while only showing relative links. | Complete
|  | As a student, I want to see student related pages in the navigation bar | Erik | There must not be any pages visible to student user that are exclusive to admin/instructor, while only showing relative links. | Complete
|  | As a professor, I want to see professor related pages in the navigation bar | Erik | There must not be any pages visible to instructor user that are exclusive to student/admin, while only showing relative links. | Complete
|  | As an admin, I want to see admin related pages in the navigation bar | Erik | There must not be any pages visible to admin user that are exclusive to student/instructor, while only showing relative links. | Complete
| As any user, I want the navigation bar to collapse according to screen size | As a user on a laptop I want the navigation bar to collapse if I change window size. | Erik | The navigation bar should collapse when the links no longer fit within the screen width. | In progress | May have strange graphical errors on login screen
|  | As a user on a smartphone, I want the navigation bar to collapse by default | Erik | The navigation bar should default to collapsed on screens too small to easily read the links. | In progress | Needs to have additional rules for smaller/larger screen sizes.
Landing Pages | As a user with account, i want a page where i can access/use the website's function | As a student, i want to have my own space to see notifications from event and more | Thuy | Page accessible and have all the features of the website for the student | In progress | Need to have more features and better looks
|  | As a instructor, i want to have my own page that i can view events, my course and notifications | Thuy | Page accessible and have all the features of the website for the instructor | In progress | Need to have more features and better looks