## Sprint 1
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 1 | Dates: Sep 3, 2015 - Sep 17, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Program Display | As a player, I want to be able to play the game in any screen sizing that I want. | As a player I want to be able to have a defualt small size on first launch. | yuchen | The program launches using the default sizing. | done
|  | As a plyaer I want to be able to select from a list of screen sizes. | yuchen | Screen sizing is implemented into the menu. | done
| As a player, I want be able to pick up items to increase the power of my weapon. | As a player I want to see clearly what the item is before picking it up. | michael | Items are consumed when the player moves over them. | in progress | implementing in progress
|  | As a player I want to be able to recognize the item without needing to pause gameplay | michael | The item is seen and moving around in the game. | pending
|  | As a player I want to see what the effect is of the weapon immediately. | michael | Weapon effects are visually seen on the client screen. | pending
User Input | As a player, I want to play with only using keyboard. | As a player, I want to use common keys for input in this game. | younouss | The player ship is responding to user input. | in progress
Data Modeling | As a player, I want to see how long I have been on the current level. |  | yuchen | The timer is connected to the interface. | done
| As a player, I want to be able to see all different ships attributes, such as: speed, weapon power, special weapons, etc. | As a player I want to see what the speed of the ship is. | will | A ship is available for use in the gameset that acts independent of the other ships. | done
| As a player, I want to know a history of my friends scores and my scores on a leaderboard, that tracks them. | As a player I want to see the weapons of the ship. | Ryan | The leader board displays with the played games. | done
Menu | As a player I want a start screen to load when the game starts |  | brian | A main screen is presented to the player on the game start. | done | polishing
| As a player I want to be able to adjust the options. | As a player I want to be able to adjust the options. | brian | Options are changed in real time after selection by the user. |  | pending
HUD | As a player, I want a simple HUD that displays my score that does not get in the way of the gameplay. | As a player I want a simple HUD that displays my score. | brian | The HUD overlays on the main level and displays content to the user. | in progress
|  | As a player I want a HUD that displays my health | brian | The HUD overlays on the main level and displays content to the user. | in progress
|  | As a player I want a HUD that displays my upgrades. | brian | The HUD overlays on the main level and displays content to the user. | in progress
Ships | As a player, I want different playable ships that feel unique. | As a player I want a default ship to be used if I am unfamiliar with the ships in the game. | will | When the game is started the default ship is created and controlable by the user. | in progress
|  | As a player, when my ship explodes, I loss all my powers but a fraction of the power ups that I collected are released in various directions. | will | Upgrades are scattered back onto the screen for re-picking up. | pending
Enemies | As a player, I want to have a variety of enemies in the game with interesting behavior. | As a player I want a easy grunt type of enemy. | will | A simple enemy is able to be used for debugging for filling the level for an easy opponent. | pending
Level | As a player, I want multiple unique levels. | As a player I want a background for the level. | ryan | The background is available and scrolls with the player movement. | pending
|  | As a player I want enemies to spawn on the screen and attack me | ryan | Enemies are able to spawn into the level given their starting coordinates. | pending
|  | As a plyer I want to be challenged on the level | ryan | Enemies are able to take more damage or move quicker on the level. | pending
|  | As a player I want to see new enemies come onto the screen | ryan | Enemies are able to move onto the screen from off screen as if out of line of sight and not appearing from magic. | pending

## Sprint 2
Sprint Backlog Template: - Rollover unclosed user stories from the preivious sprint. - Add some of high priority user stories (epics) from Product Backlog for this sprint
Sprint 2 | Dates: Feb. 12, 2015 - Feb. 19, 2015
Category | EPIC (user stories in the initial Product Backlog) | Tasks (Child user stories) | Assigned To | Acceptance criteria | Status | Notes (Roadblock, etc)
Event Managment | As a professor I want to create an event so that other people may scheduel time with me | As a professor I want to have an event creation page so that I can create a new event | Lynn | Page is accessible | Completed
|  | As a professor I want a newly created event to be permenatly stored, so that I and others can view events later | Lynn | When form is submited, a Proper Database record is strored | Incomplete | Faculty ID is not stored in the record yet
|  | As an proffessor I want to view my created events, so that I can know which events have been created | Lynn | Page is accessible, and nicely styled | Incomplete | More Styling Needed
| As a proffesor, when I create an event I want the right amount of timeslots to be automatically created, so that other can view the available timeslots | As a proffesor I want the number of time slots for an event to be automatically calculated so that I don't have to create individual slots myself | Lynn | Amount of slots are properly calculated and insterted in to the database | Completed
|  | As a proffesor I want to be able to view the timeslots for each event | Lynn | Slots for each Event, are displayed and nicely styled | Incomplete | More Styling needed
Login page | As a student I want to be able to login so that I can access my profile
|  | As a student I want to be able to login to the system so that I can access my profile | Stanislav | Student inputed the credentials and was able to access the profile | Completed
As an instructor I want to be able to login so that I can access my profile
|  | As a instructor I want to be able to login to the system so that I can access my profile | Stanislav | Instructor inputed the credentials and was able to access the profile | Completed
As an administrator I want to be able to login so that I can access my profile
|  | As a administrator I want to be able to login to the system so that I can access my profile | Stanislav | Instructor inputed the credentials and was able to access the profile | Completed
Registration page | As a professor I want to register so that I can utilize the services provided by CS website
|  | As an administrator I want to be able to add an instructor to the system so that he can start using the CS website | Stanislav | When form is submited the input verified If valid information is submitted a new user is created in the database | Not implemented | User roles not implemented yet.
As a student I want to register so that I access services provided by CS website
|  | As a student I want to be able to submit a registration request to the system so that I receive a confirmation email from the system | Stanislav | Registration request was successfully submitted and email with the confirmation link received | Not implemented
|  | As a student I want to be able to receive an email so that I can confirm my email address is a valid email address | Stanislav | Confirmation link was received. Upon opening the link, student was verified and able to access their profile | Not implemented
Texbook Database | As a student, I want to have a convinient way to see the texbooks reqired for courses I am interested in
|  | As a student I want to search for specific classes to see the required text | Brian |  | Complete
|  | As a student I want to be able to see the required text for all available classes on one page | Brian |  | Complete
Chat page | As a professor, I want to allow my students to be able to ask me questions instantly when I am available so that I can better help them. | As a professor I want to have a chat webpage so that I can send chat messages | Travis | There must be a page available to professors to enter messages | In progress | Basic chat mechanism implemented. Individual user roles not implemented. The chat is open to all users. Bugs from sprint 1 fixed.
|  | As a professor I want to have a chat interface so that I can send chat messages | Travis | Professors must have an interface for entering messages | In progress
|  | As a professor I want to be able to send chat messages so that all the participants of the chat can see them | Travis | Messages must be sent to all other chat participants | In progress
|  | As a professor I want to specify my name so that participants can easily identify me | Travis | Messages must include a user name | In progress
|  | As a professor I want to be able to see my chat history so that I can see what I discussed with my students | Travis | Chat history must be saved for the chat session | In progress
| As a student, I want to be able to ask my professors questions instantly when they are available so that I can get help when I need it. | As a student I want to have a chat webpage so that I can send chat messages | Travis | There must be a page available to students to enter messages | In progress | Basic chat mechanism implemented. Individual user roles not implemented. The chat is open to all users. Bugs from sprint 1 fixed.
|  | As a student I want to have a chat interface so that I can send chat messages | Travis | Students must have an interface for entering messages | In progress
|  | As a student I want to be able to send chat messages so that all the participants of the chat can see them | Travis | Messages must be sent to all other chat participants | In progress
|  | As a student I want to specify my name so that participants can easily identify me | Travis | Messages must include a user name | In progress
|  | As a student I want to be able to see my chat history so that I can see what I discussed with my professors | Travis | Chat history must be saved for the chat session | In progress
Navigation Bar | As a user, I want to see pages that are related to my user role. | As an unregistered user, I was to see the other pages I can navigate to. | Erik | There must not be any pages visible to unregistered user that are exclusive to student/admin/instructor, while only showing relative links. | Complete
|  | As a student, I want to see student related pages in the navigation bar | Erik | There must not be any pages visible to student user that are exclusive to admin/instructor, while only showing relative links. | Complete
|  | As a professor, I want to see professor related pages in the navigation bar | Erik | There must not be any pages visible to instructor user that are exclusive to student/admin, while only showing relative links. | Complete
|  | As an admin, I want to see admin related pages in the navigation bar | Erik | There must not be any pages visible to admin user that are exclusive to student/instructor, while only showing relative links. | Complete
| As any user, I want the navigation bar to collapse according to screen size | As a user on a laptop I want the navigation bar to collapse if I change window size. | Erik | The navigation bar should collapse when the links no longer fit within the screen width. | In progress | May have strange graphical errors on login screen
|  | As a user on a smartphone, I want the navigation bar to collapse by default | Erik | The navigation bar should default to collapsed on screens too small to easily read the links. | In progress | Needs to have additional rules for smaller/larger screen sizes.
Landing Pages | As a user with account, i want a page where i can access/use the website's function | As a student, i want to have my own space to see notifications from event and more | Thuy | Page accessible and have all the features of the website for the student | In progress | Need to have more features and better looks
|  | As a instructor, i want to have my own page that i can view events, my course and notifications | Thuy | Page accessible and have all the features of the website for the instructor | In progress | Need to have more features and better looks